## Slide 1
Introduction to
Project Management
Michael Vidalis

## Slide 2: Learning Objectives
Describe project management objectives
Describe the project life cycle
Diagram networks of project activities
Estimate the completion time of a project
Compute the probability of completing a project by a specific time

## Slide 3: Defining a Project
What is a project?
  Any unique endeavor with specific objectives
  With multiple activities
  With defined precedent relationships
  With a specific time period for completion
Examples?
  A major event like a wedding
  Any construction project
  Designing a political campaign
Projects are processes that are performed infrequently and ad hoc, with a clear specification of the desired objective.

## Slide 4
A project has a single objective that must be accomplished through the completion of tasks that are unique and interrelated
Projects are completed through the deployment of resources
Projects have scopes, schedules, and costs and are accomplished within specific deadlines, budgets, and according to specification
What is a Project?

## Slide 5: Examples of Projects
Constructing highways, bridges, tunnels and dams
Erecting skyscrapers, steel mills, and homes
Organizing conferences and conventions
Managing R&D projects
Running political campaigns, war operations, and advertising campaigns

## Slide 6: Project Life Cycle
Conception: identify the need
Feasibility analysis or study: costs benefits, and risks
Planning: who, how long, what to do?
Execution: doing the project
Termination: ending the project

## Slide 7: Life Cycle of a Project (Stretched-S) & (Exponential)

## Slide 8: Background for Project management
Project management concerned with managing organizational activities.
Often used to integrate and coordinate diverse activities.
Projects are special types of processes.

## Slide 9: What is Project Management?
a method for organizing tasks
a structured framework to help a group work productively
tools to aid in task sequencing, dependency analysis, resource allocation, scheduling, etc.
tools to track progress relative to plan
Monitoring and controlling
Reporting
Continually striving to improve the process

## Slide 10: Why Need Project Management?
Complex project needs coordination of:
  Multiple people
  Multiple resources (labs, equipment, etc.)
  Multiple tasks – some must precede others
  Multiple decision points – approvals
  Phased expenditure of funds
  Matching of people/resources to tasks

## Slide 11: Phases of Project Management
Define the project’s scope
Develop the project’s plan
Implement the plan & control the process
Close out the project

## Slide 12: Suggested Steps in Project Management
Generate a formal definition of the project, with goals, constraints, assumptions
Identify project start/end dates, any mandatory milestones, including reports, signoffs, deliverables, etc.
List constraints – money, equipment availability, holidays, etc.
Identify tasks to be accomplished – high level (i.e., by categories), then details within each, using brainstorming method – green light

## Slide 13: Suggested Steps, cont.
Refine detailed task list, dropping/ combining, adding things omitted
Then, for each task in list:
Estimate time (person hours, calendar period)
Identify dependencies among tasks
Identify resources (people, money, parts, etc.)

## Slide 14: Suggested Steps, cont.
Organize task groups roughly by starting date
List dependencies that should or MUST hold
Use MS Project to make a GANTT chart
First capture tasks and task groups, milestones
Identify critical path, see if it can be shortened (get more “slack”)
Assign person-hours and specific team member(s) to each task – identify “task leads”

## Slide 15: Suggested Steps, cont.
As project progresses:
Monitor, record progress on all tasks, at least weekly – use “Tracking Gantt Chart”
Pay particular attention to those on critical path
Revise plan as needed to take into account changes, adapt to meet milestones

## Slide 16: Planning and Scheduling Projects
Planning. Determining what must be done and which tasks must precede others.
Scheduling. Determining when the tasks must be completed;
when they can and when they must be started;
which tasks are critical to the timely completion of the project; and
which tasks have slack and how much.

## Slide 17: Scheduling the Project: PERT and CPM

## Slide 18: Develop the Project’s Plan
Break Down Project
Tasks (WBS)
Time Estimation &
Dependencies
Determine Resource
Needs
Develop Gantt Chart
Review & adjust
Notes: Planning is an iterative process. Some projects won’t require a proposal

## Slide 19: What is a Work Breakdown Structure (WBS)?
A hierarchical representation of activities
It starts with the major project areas to be accomplished
It breaks the project areas into actionable pieces of work, segmenting elements into appropriate sublevels

## Slide 20: WBS – Activity Levels
Level 1 – Identify major objective areas or categories
Level 2 – Begin to divide the areas into sub-tasks
Level 3 – Continue to break down the sub-tasks into actionable items
The lowest level associated with a branch in the hierarchy is referred to as a “work package”
# of levels depends on project complexity

## Slide 21: Terminology
Activity
Event
Network
Path
Critical Path
Critical Activities

## Slide 22: Network Diagrams
Activity-on-Node (AON):
  Uses nodes to represent the activity
  Uses arrows to represent precedence relationships

## Slide 23: Network Diagrams
Activity-on-Arc (AOC):
  Uses arcs to represent the activity
  Uses nodes to represent precedence relationships
Activity A precedes activity B
1
2
A
3
B

## Slide 24: Project Planning When Activity Times are Known
Inputs
  list of the activities that must be completed
  activity completion times
  activity precedence relationships

## Slide 25: Project Planning When Activity Times are Known continued
Outputs
  graphical representation of project
  time to complete project
  identification of critical path(s) and activities
  activity and path slack
  earliest and latest time each activity can be started
  earliest and latest time each activity can be completed

## Slide 26: Example

## Slide 27: Network Diagram

## Slide 28: Early Start and Finish Times

## Slide 29: Latest Start and Finish Times

## Slide 30: Activity Slack Time
TES = earliest start time for activity
TLS = latest start time for activity
TEF = earliest finish time for activity
TLF = latest finish time for activity
Activity Slack = TLS - TES = TLF - TEF

## Slide 31: Path Slack
Duration of Critical Path
- Path Duration
Path Slack

## Slide 32: Activity Slack Times

## Slide 33: Project Scheduling and Tracking
  Scheduling is the process of deciding:
    In what sequence a set of activities will be performed.
    When they should start and be completed.
  Tracking is the process of determining how well you are sticking to the cost estimate and schedule.

## Slide 34: Some Basic Project Management Terminology
Deliverable: some concrete thing which is to be delivered, to the client or internally to the development team; e.g.
  Specifications reports
  Executable program
  Source code
Task/Activity: something we have to do during the project; e.g.
  Defining user requirements
  Coding a module
  Doing system testing
Each task or activity will take some length of time
  Referred to as duration of task
  Sometimes measured in days, weeks, etc.
  Sometimes measured in person-days, person-weeks, etc.
  Person-day = number of people X number of days
    Example: 12 person days for writing all code could mean 1 person 12 days or 4 people 3 days
    Note: not always true that a task that takes 1 programmer 12 days would take 12 programmers 1 day

## Slide 35: Dependencies and Milestones
For a given task or activity, may be impossible to start it without some other task(s) or activity(ies) having been completed; e.g.
  Cannot start coding without completing design
  Cannot start system testing without completing code integration and test plan
If task B cannot start without A being completed, we say
  B depends on A
  There is a dependency between A and B
Milestone: some achievement which must be made during the project; e.g.
  Delivering some deliverable
  Completing some task
Note, delivering a deliverable may be a milestone, but not all milestones are associated with deliverables

## Slide 36: Setting and Making Deadlines
Deadline time by which milestone has to be met
  Some deadlines are set by the client
  Others are set by us on project to make sure project stays on track
To set a deadline for completing task T, we must consider how long it will take to:
  Complete the tasks that task T depends on
  Complete task T itself
If we miss a deadline, we say (euphemistically) “the deadline has slipped”
  This is virtually inevitable
Important tasks for project managers
  Monitor whether past deadlines have slipped
  Monitor whether future deadlines are going to slip
  Allocate or reallocate resources to help make deadlines
PERT chart and Gantt charts help project managers do these things (among others)

## Slide 37: Project Management Using Microsoft Project
Allows many different ways of entering and observing information
includes many features to help identify problems with a plan
regular use can help a group refine plans to make meeting targets more realistic

## Slide 38: Our “Flyover” of Project 2010
Adding tasks, durations
Setting dependencies
Seeing critical path, etc.
“Rolling up” subtasks
Assigning resources
Adjusting durations, time assignments, etc.

## Slide 42: Our “Flyover” of Project 2010
Adding tasks, durations
Setting dependencies
Seeing critical path, etc.
“Rolling up” subtasks
Assigning resources
Adjusting durations, time assignments, etc.

## Slide 46: Our “Flyover” of Project 98
Adding tasks, durations
Setting dependencies
Seeing critical path, etc.
“Rolling up” subtasks
Assigning resources
Adjusting durations, time assignments, etc.

## Slide 51: WATCH YOUR DEPENDENCY CHOICES!!!
If you choose something other than the “default” finish/start constraints, you will probably LOSE your ability to track the critical path
So AVOID “finish by” or “start by” with particular calendar dates, or other types of constraints.
Break tasks apart as needed, in order to make finish/start constraints realistic!

## Slide 52: Our “Flyover” of Project 2010
Adding tasks, durations
Setting dependencies
Seeing critical path, etc.
“Rolling up” subtasks
Assigning resources
Adjusting durations, time assignments, etc.

## Slide 66: Our “Flyover” of Project 2010
Adding tasks, durations
Setting dependencies
Seeing critical path, etc.
“Rolling up” subtasks
Assigning resources
Adjusting durations, time assignments, etc.

## Slide 78: Our “Flyover” of Project 98
Adding tasks, durations
Setting dependencies
Seeing critical path, etc.
“Rolling up” subtasks
Assigning resources
Adjusting durations, time assignments, etc.

## Slide 84
YOUR MS Project has a “Deadline” box
on this page! Use it to let you get warned when something gets pushed back too far, but STILL not assigning a “start no earlier than” or “finish no later than” constraint to it – still using “As soon as possible.”

## Slide 89: Management of YOUR Project
With your team members
Create a plan for the entire project
Set milestones for tracking progress
Provide more detail for near-term tasks
Use with your facilitator to report progress and revise/add detail to plan
Assign specific tasks to team members
Revise plan and activities as required to achieve objectives